## Sprints
Week | Tasks | Initiated?
Sprint 1
Objective | Foundation setup and initial design
Week 1 | Finalize project idea and requirements | Y
Week 1 | Set up project repo and collaborative tools | Y
Week 1 | Design initial wireframes for the UI (simple static design) | Y
Week 1 | Initiate basic frontend and backend project structure | Y
Deliverable | Basic app structure outline, basic design and wireframes, assignment doc first draft
Sprint 2
Objective | Focus on defining core features and assignment doc submission + repo collab test runs
Week 2 | Add details and finalise wireframes & UI mockups | y
Week 2 | plan API structure | Y
Week 2 | continue with basic front-end and back-end structure | y
Week 2 | Complete Part 1 of Assignment task (aims, requirements, tools, features) | Y
Week 2 | Complete Part 2 of Assignment task(design and wireframes) | y
Week 2 | Complete Part 3 of Assignment task(repo, contribution from all members) | Y
Week 2 | Complete Part 4 of the Assignment task (submission) | Y
Deliverable | Design finalised, assignment doc and repo content submission, clear vision of core features
Sprint 3
Objective | Integrating APIs and building core features
Week 3 | Develop features: FrontEnd HTML and CSS
Week 3 | Develop features: 3rd party API integration
Week 3 | Develop features: continue user form validation and authentication/authorisation
Week 3 | Develop features: build APIs to interact with DB
Week 3 | Develop features: create and intergate DB
Week 3 | Develop features: any outstanding UI support?
Deliverable | Movie recommendations set up, basic authentication flow
Sprint 4
Objective | Feature completion and testing
Week 4 | Finalise core features
Week 4 | Refine UI/UX based on feedback
Week 4 | Start work on testing functionality
Week 4 | Implement any additional features if time permits (search/filter etc)
Week 4 | Handle Edge-cases and debug
Week 4 | Start work on Project Document first draft
Deliverable | Complete movie collection feature, improve UI, basic testing
Sprint 5
Objective | Testing, documentation, finalise UX/UI, prepare presentation
Week 5 | Work on README file
Week 5 | Finalize user interface and ensure responsiveness
Week 5 | Perform in-depth testing of all features
Week 5 | Final testing, bug fixing, documentation, and final submission
Week 5 | Prepare presentation slides
Week 5
Deliverable | Fully functional app with all core features, project submission, demo and presentation

## Workload Allocation
Team
Tasks | Sadie | Victoria | Kiki | Alberta | Safa | Jess
Assignment Document management | X
Github Repo management
Figma wireframes and design |  |  | X
CSS | X |  | X
Plan API structure and 3rd party API integration |  | X | X
Components js |  | X |  | X | X
Back-end logic |  | X |  |  | X | X
SQL lead |  |  |  |  | X | X
Lead on testing | X |  |  |  |  | X
Lead on Project document |  | X | X
Project README |  |  |  |  | X
Submissions |  | X
Presentation slides |  |  |  | X |  | X
Project accessibility | X |  |  | X
Team
| Sadie | Victoria | Kiki | Alberta | Safa | Jess
Week 5 detailed tasks
Sign In page get to work |  |  |  | X
Sign up page to fully test
Connect age from user profile to movie suggestion |  | X
ProfilePage get to work |  |  |  |  | X
landing page guest option |  |  | X
option to change location on the suggestion page
watchlist