## Activity Log - Sadie Jones
Name: Sadie Jones |  | Project Group (Name/Number): Group-4-Fullstack
This activity log is for you to document your individual contributions and ideas you have done towards your final group project. This will be submitted to your instructors along with your project code. You can document how many minutes you spent working on your code, when you had team meetings outside of the class sessions, or use this as a way to take notes for your own viewing. This is to be completed individually.
Week: | Date: | Activity/Task: | Time spent on Activity: | Team Members Involved (if applicable) | Completed? | Notes:
1 | 31/03/2025 | Zoom team call : intros, SWOT analysis, initial ideas and areas of interest | 45 minutes | Sadie, Viktoria, Alberta, Ana(Kiki) | Yes | prepare to pitch project idea
1 | 2025-01-04 | Zoom team call to pitch ideas and pick one for the project, initial discussion of assignment requirements and allocation of tasks | 60minutes | Sadie, Viktoria, Alberta, Ana(Kiki), Safa | Yes | I need to - Initiate the assignment document. Viktoria to create a repo, everyone to check out API tools we have selected to use, Kiki to start work on wireframes
1 | 2025-03-04 | Researched openweathermap API, and attempted test setup, | 90 minutes | Sadie | Yes | shared with team
1 | 2025-06-04 | Added .gitignore to repo - for holding purposes | 10 minutes | Sadie | Yes | added to github
2 | 2025-07-04 | Created and uploaded project assignment document for task 1 to google documents, instructed to move onto task 2 | 2 hours | Sadie | Yes | added to google documents
2 | 2025-07-04 | Zoom team call : discussing roles for the assignment and areas of focus, reviewing pitch doc and wireframes, planning parts 3 and 4 | 45 minutes | Sadie, Viktoria, Alberta, Ana(Kiki), Safa, Jess | Yes | Update css for our project app.js
2 | 2025-09-04 | Tested sample CSS glass effect for project | 50 minutes | Sadie | Yes | shared with team
2 | 2025-09-04 | Zoom team call : reviewing work done on parts 1, 2 and 3, Allocating roles for the main app, forming smaller sub-teams to collectively complete tasks | 20 minutes | Sadie, Viktoria, Alberta, Ana(Kiki), Safa, Jess | Yes | All roles provisionally assigned
2 | 2025-09-04 | Edited CSS for project assignment documents and added my information | 60 minutes | Sadie | Yes | asked for a pull request
2 | 2025-10-04 | Edited project assignment to include names and short summary for design choices (task 2) | 30 minutes | Sadie | Yes | asked for review from Kiki on summary
2 | 2025-11-04 | Merged pull requests, Fixed css bug, object bug in app.js and uploaded to github | 30 minutes | Sadie | Yes | asked for review on bug fix
2 | 2025-11-04 | Uploaded pdf of project assignment to github | 5 minutes | Sadie | Yes | shared with team
3 | 16/04/2025 | Feedback from Fredrick. Creation of a spreadsheet for flow to be made. Then, we will research marrying up the front and back end. Spoke about folder structure | 50 minutes | Sadie, Viktoria, Alberta, Safa, Jess | Yes | Create google spreadsheet. Research front and back end marrying up. Add file format to repo
3 | 16/04/2025 | Created Google spreadsheet for flow tracking | 5 minutes | Sadie | Yes | informed group
3 | 17/04/2025 | Looked into cors and how to get it to work | 50 minures | Sadie | No | Can get coordinates but cant marry front and back end.
3 | 18/04/2025 | Managed to get user location using browser geolocation and created api to show weather | 30 minutes | Sadie | Yes | Shared with group
3 | 19/04/2025 | Started to dissect the Figma wireframe. | 50 minutes | Sadie | No | Continue with other pages
4 | 21/04/2025 | Worked on weatherapi and uploaded it to repo. Included creating .env and some folder structure. Spoke with Viktoria to merge and add movie api. | 3 hours | Sadie | Yes | Will discuss at group
4 | 23/04/2025 | Merged and checked Viktorias API | 10 minutes | Sadie | Yes | Successful merge
4 | 25/04/2025 | Helped Kiki with branch bugs | 30 minutes | Sadie, Kiki | Yes | Successful merge
4 | 26/04/2025 | Updated sign up page and css. Added background override, fixed bugs | 5 hours | Sadie | Yes | Successful merge and spoke to group
4 | 27/04/2025 | Updated CSS on sign up page, fixed sign up data and database. adapted backgroundwrapper to include overrides. Added link to sign up page to sign in. | 3 hours | Sadie | Yes | Constant contact with Viktoria and attempts made in group chat
5 | 2025-01-05 | Fixed Albertas code and merged to main. Fixed links where sign in did not point to correct place, fixed bugs, multiple conversations had with Viktoria. Updated team | 6 hours | Sadie | Yes | Constant contact with Viktoria and attempts made in group chat
5 | 2025-01-05 | Zoom call with teams, updated and suggested tasks to do | 10 mins | Alberta, Sadie, Safa, Kiki,Viktoria | Yes | css tasks split between myself and Kiki
5 | 2025-03-05 | Attempted testing got some to work but did not on Viktorias side. Focused on sign in/sign up and profile page. Updated logic to update information on the page. Added protected routes, removed access to website if not logged in. Altered how the logout button appears. Multiple conversations had with Viktoria to progress through and complete our web application, looked through pull requests and tried to debug. Couldnt so built new logic. | 14 hours | Sadie | Yes | Constant contact with Viktoria and attempts made in group chat
5 | 2025-04-05 | Zoom team call : catch up with Viktoria and Kiki (the only available team members) to discuss the urgent fixes and the last bits to work on before submission | 20 minutes | Sadie, Viktoria, Kiki | Yes | members taken notes
5 | 2025-04-05 | Completed all css. Ensured that it was working efficiently. Used parts of kikis code for css, as unable to merge due to file changes. Ensured my branch was merged to main at all times. Fixed age certification bug where the decade filter would ignore the user's age. merged branches and fixed CSS bugs | 14 hours | Sadie | Yes | Constant contact with Viktoria and attempts made in group chat
Total time:

## Activity Log - Viktoria Lauri
Name: Viktoria Lauri |  | Project Group (Name/Number): Group-4-Fullstack
This activity log is for you to document your individual contributions and ideas you have done towards your final group project. This will be submitted to your instructors along with your project code. You can document how many minutes you spent working on your code, when you had team meetings outside of the class sessions, or use this as a way to take notes for your own viewing. This is to be completed individually.
Week: | Date: | Activity/Task: | Time spent on Activity: | Team Members Involved (if applicable) | Completed? | Notes:
1 | 31/03/2025 | Zoom team call : intros, SWOT analysis, initial ideas and areas of interest | 45 minutes | Sadie, Viktoria, Alberta, Ana(Kiki) | Yes | prepare to pitch project idea
1 | 2025-01-04 | Zoom team call to pitch ideas and pick one for the project, initial discussion of assignment requirements and allocation of tasks | 1 hour | Sadie, Viktoria, Alberta, Ana(Kiki), Safa | Yes | Sadie to initiate the assignment document, me to create a repo, everyone to check out API tools we have selected to use, Kiki to start work on wireframes
1 | 2025-01-04 | Setting up Google Drive share folder and adding team members with editor permission, adding CFG project related guides/docs | 15minutes | Viktoria | Yes | Folder to be use for editing documentation and collecting suggestions
1 | 2025-02-04 | Creating Project Plan doc, Project activity Log, sharing ideas on Slack on design and core features | 1 hour | Viktoria | Yes | Awaiting feedback on my suggestions
1 | 2025-06-04 | Creating GitHub repo | 15minutes | Viktoria | Yes | Awaiting invite acceptance from team
2 | 2025-07-04 | Zoom team call : discussing roles for the assignment and areas of focus, reviewing pitch doc and wireframes, planning parts 3 and 4 | 45 minutes | Sadie, Viktoria, Alberta, Ana(Kiki), Safa, Jess | Yes | Leading part 3 and contributing to the assignment doc
2 | 2025-09-04 | Creating the test run app, attempting CSS, coding App.js content, pushing to GitHub; also reviewing the pitch doc and making additions/suggestions for content | 1.5 hours | Viktoria | Yes | Awaiting review on my PR
2 | 2025-09-04 | Zoom team call : reviewing work done on parts 1, 2 and 3, discussions and retros; allocating roles for the main app, forming smaller sub-teams to collectively complete complex tasks | 20 minutes | Sadie, Viktoria, Alberta, Ana(Kiki), Safa, Jess | Yes | All roles provisionally assigned
2 | 2025-11-04 | Fixed bugs, reviewed PRs and resolved conflicts, submitted assignment doc and repo | 30min | Viktoria | Yes | Assignment submitted on time
3 | 16/04/2025 | Zoom team call : receiving feedback from Fredrick on the assignment doc, discussing flow | 30 minutes | Sadie, Viktoria, Alberta, Ana(Kiki), Safa, Jess | Yes | more clarification on allocating tasks, good feedback received on the project plan
3 | 19/04/2025 | Looked into the TMDB docs and endpoints, experimented with returning json objects with information | 1 hour | Viktoria | Yes | object contains the info required, now need to figure out to make calls from backend
4 | 21/04/2025 | Created the folder structure for client and server side of the project, initiated package.json files for each part and the root, installed helper dependencies (axios, nodemon, concurrently, dotenv, express, cors), pushed, PR, cleaned up the old repo structure to include Sadie's updates. | 2 hours | Viktoria | Yes | ready for discussion at our team call on Tue 22/04
4 | 21/04/2025 | Created the working TMDB API endpoint on server side that calls 3rd party API and returns the randomly selected movie in a chosen genre. Merged branches with Sadi's input and pushed my code in a PR | 2 hours | Viktoria | Yes | waiting for other team members to test it out and merge
4 | 22/04/2025 | Created and filled out partically the Project Document, Background section and the Intro nearly done, rest is summarised in bulletpoints for now to fill out at the end of the project | 1 hour | Viktoria | Yes | Awaiting review from team
4 | 22/04/2025 | Zoom team call : disussing new architecture of the app and who is taking which components | 30 minutes | Sadie, Viktoria, Alberta, Ana(Kiki), Safa, Jess | Yes | have until Fri to build what has been allocated to me
4 | 23/04/2025 | Built out the logic to connect weather and movie data in a way that: movie genres are picked according to the weather at user's location, then a movie is picked from a a random selection from the genres, a separate API call is made to fetch certification for the picked movie ID and that certification is checked against userAge. If checks pass, then movie data is approved to be passed on to frontend. Used a few util modules, services, controllers, routes to connect all in one. Then managed to separate user geolocation global state into context and use it in both WeatherDisplay and RecommendMovie modules, which now successfully render on screen. | 5 hours | Viktoria | Yes | waiting for other team members to test it out and merge
4 | 24/04/2025 | Built a suggestion shuffle button, used it and discovered our movie array is only limited to 20 results on that API endpoint if we don't use the page filter, so fixed the bug and inegrated page randomiser to expand movie pool to 1000+. Also worked out and built the util to map genre IDs from the movie object to genre names on client side. | 2 hours | Viktoria | Yes | pushed to repo awaiting testing from other team members
4 | 27/04/2025 | Reviewed Safa's PR and tested code on her branch, continued building and connecting services. Re-arranged files in the client/src folder, moved App.js from the pages into the root, cleaned App.js to just contain routes to pages components, introduced routes, route, etc. Renamed all page components in line with best practice, created the landing page, connected it to signup, signin pages and temporarily to the dashboard. Took out movie back-end API call into shared state (context), connet this to both dashboard and the new page for movie details, pulled all movie details from movie object, arrange local storage for the fetched suggestion, created logout logic in the shared state file to clear all user-related stored data on logout, created the Logout button in Navbar. | 5 hours | Viktoria | Yes | pushed to repo awaiting testing from other team members
5 | 29/04/2025 | Went to check Safa's new PR, found it was with errors, checked main branch and also errors app not compiling! Spend a long time figuring out what has gone wrong. Found that git does not count casing amends in file names as changes, needed to rename 3 times the whole of pages section to get git, gitHub and file names sycned properly and folders not duplicated. | 1 hour | Viktoria | Yes | pushed to repo awaiting testing from other team members
5 | 29/04/2025 | Zoom team call : disussing what is left to build, checking which code in PRs runs with errors and why. | 30 minutes | Sadie, Viktoria, Alberta, Ana(Kiki), Safa | Yes | members taken notes
5 | 29/04/2025 | Needed to fix the bug where movie re-fetches on back button click, which was not expected behaviour. Fixed. Worked on release_by_year filter buttons, which needed code on both backend for fetching and filtering and front-end for selecting and sharing state between components. Difficult and tricky task with lots of bug fixes needed. Finally done and all working | 4 hours | Viktoria | Yes | pushed to repo awaiting testing from other team members
5 | 30/04/2025 | Zoom team call : catch up what remains to work on, not very productive as half of the team couldn't make it | 15 minutes | Sadie, Viktoria, Alberta | Yes | members taken notes
5 | 30/04/2025 | Reviewed Kiki's changes, looked into how to reverse changes, as code buggy and merged into main, in contact with Kiki on how to improve code. Working on Safa's branch to test out the sign up process, errors coming up, looking into ways to fix, working on connecting sign up process with database. Patching vars, adding missed dependencies, merged changes and resolved merge conflicts. Had huge difficulty to get data flow from sign up to db, explored alternative solutions to SQL as little response from team on testing out the code. Identified JSON as a good alternative, awaiting feedback. Checkout out Sadie's branch to review styling. | 4 hours | Viktoria | Yes | awaiting feedback from other team members
5 | 2025-01-05 | Problems with SQL workbench and VSCode, sockets pointing to different instances, spent A LOT of time trying to fix, managed to run SQL in VSCode and had to settle for that! At least I managed to get the data flow to work and reflect on the database. Success! Figured out how JWT tokens work, password hashing works well, sessions persist data for the logged in user. Starting setting up environment for testing, had a real struggle for a few hours, deleted the branch in frustration. Reviewed outstanding features and nudget team. By the evening another difficulty with database connecting. Reviewed Safa's profile page branch and identified missing logic, asked Safa to improve. Clarified what we need to have in the profile form. | 5 hours | Viktoria | Yes | awaiting feedback from other team members
5 | 2025-01-05 | Zoom team call : catch up what remains to work on, discuss testing frameworks, styling, core features and flaws | 15 minutes | Sadie, Viktoria, Alberta, Kiki | Yes | members taken notes
5 | 2025-02-05 | Merged whatever working code we have into main, resolved conflicts. Loked into feedback on my features, made sure smooth code run. Jumped on Safa's profile page code to help out and accelerate the process. Had a full on experience debugging teammate's code, followed through and altered vars and logic, found and fixed bugs. Learned a few things about working on someone's branch where your colleague is also working on the same branch, commit reverse and all that! Managed to get Safa's code to finally work. Also managed to write a test that passes on the back end. Cross checked our product against project brief, source code brief, identified points of improvement. | 6 hours | Viktoria | Yes | awaiting feedback from other team members
5 | 2025-03-05 | Rewvied Sadie's branch and tested, testing fails, spent time to attempt fixing, really difficult, something to do with config, jest not reading imports correctly, spent hours (just like Sadie) to try get these to work. Only managed 1 working test. Had a call with Sadie and decided to move on from testing as need to work on other aspects of the project. On call with Sadie for support with merging difficulty, managed to resolve collectively, tested Sadie's updates on Safa's branch and working brilliantly, merged and resolved conflicts with main. | 6 hours | Viktoria | Yes | awaiting feedback from other team members
5 | 2025-04-05 | Zoom team call : catch up with Sadie and Kiki (the only available team members) to discuss the urgent fixes and the last bits to work on before submission | 20 minutes | Sadie, Viktoria, Kiki | Yes | members taken notes
5 | 2025-04-05 | Checked Sadie's branch and latest update on styling and functionality, merged. Discussed Kiki's input. Worked on user age being fetched from SQL and passed on to frontend via api, used in userContext and shared with other components to fetch appropriate movie with the right certification. Improved most of the sections of the project document, worked with Kiki on architecture design diagram. Worked on objectives vs final result in conclusion explicitly. Changed README to provide clearer instructions for installation and use. Final check against project brief. Prepared docs for submission, improved code readability and comments. Uploaded project documentation to repo, submitted project before submission deadline. | 12 hours | Viktoria | Yes | awaiting feedback from other team members
Total time:

## Activity Log - Ana(Kiki) Villar
Name: |  | Project Group (Name/Number): Group-4-Fullstack
This activity log is for you to document your individual contributions and ideas you have done towards your final group project. This will be submitted to your instructors along with your project code. You can document how many minutes you spent working on your code, when you had team meetings outside of the class sessions, or use this as a way to take notes for your own viewing. This is to be completed individually.
Week: | Date: | Activity/Task: | Time spent on Activity: | Team Members Involved (if applicable) | Completed? | Notes:
1 | 31/03/2025 | Zoom team call : intros, SWOT analysis, initial ideas and areas of interest | 45 minutes | Sadie, Viktoria, Alberta, Kiki | Yes | prepare to pitch project idea
1 | 2025-01-04 | Zoom team call to pitch ideas and pick one for the project, initial discussion of assignment requirements and allocation of tasks | 60 minutes | Sadie, Viktoria, Alberta, Kiki, Safa | Yes | Sadie to initiate the assignment document, me to create a repo, everyone to check out API tools we have selected to use, Kiki to start work on wireframes
1 | 04-05/04/2025 | Worked on wireframe design in Figma | 2 hours | Kiki |  | Created wireframes based on discussion we had in our meeting
2 | 2025-07-04 | Zoom team call : discussing roles for the assignment and areas of focus, reviewing pitch doc and wireframes, planning parts 3 and 4 | 45 minutes | Sadie, Viktoria, Alberta, Kiki, Safa, Jess | Yes | Leading part 3 and contributing to the assignment doc
2 | 08-09/04/2025 | Added user flows, screens and answered the questions for part 2 in the Design tab in the deliverable document | 1 hour | Kiki | Yes
2 | 2025-09-04 | Made some amends to the prototype in Figma and added prototype workflow to make buttons clickable | 30 minutes | Kiki | Yes
2 | 2025-09-04 | Zoom team call : reviewing work done on parts 1, 2 and 3, discussions and retros; allocating roles for the main app, forming smaller sub-teams to collectively complete complex tasks | 20 minutes | Sadie, Viktoria, Alberta, Kiki, Safa, Jess | Yes | All roles provisionally assigned
2 | 2025-10-04 | Updated the file in github | 25 mins | Kiki | Yes | Added my card
4 | 30/05/2025 | Landing page guest location feature | 2 hours | Kiki | No
4 | 2025-01-05 | Landing page CSS | 2.5 hours | Kiki | Yes
5 | 2025-02-05 | Landing page guest location feature | 2 hours | Kiki | No | I could not manage to get the movie recommendation page to show a selected location as a guest user, instead of fetching from the location
5 | 2025-03-05 | Movie recommendation CSS + Movie information CSS | 3 hours | Kiki | Yes
5 | 2025-04-05 | Movie information CSS | 2 hours | Kiki | Yes
Total time:

## Activity Log - Alberta Uwadiae
Name: |  | Project Group (Name/Number): Group-4-Fullstack
This activity log is for you to document your individual contributions and ideas you have done towards your final group project. This will be submitted to your instructors along with your project code. You can document how many minutes you spent working on your code, when you had team meetings outside of the class sessions, or use this as a way to take notes for your own viewing. This is to be completed individually.
Week: | Date: | Activity/Task: | Time spent on Activity: | Team Members Involved (if applicable) | Completed? | Notes:
1 | 31/03/2025 | Zoom team call : intros, SWOT analysis, initial ideas and areas of interest | 45 minutes | Sadie, Viktoria, Alberta, Kiki | Yes | prepare to pitch project idea
1 | 2025-01-04 | Zoom team call to pitch ideas and pick one for the project, initial discussion of assignment requirements and allocation of tasks | 60minutes | Sadie, Viktoria, Alberta, Ana(Kiki), Safa | Yes | Sadie Initiate the assignment document. Viktoria to create a repo, everyone to check out API tools we have selected to use, Kiki to start work on wireframes
2 | 2025-07-04 | Zoom team call : discussing roles for the assignment and areas of focus, reviewing pitch doc and wireframes, planning parts 3 and 4 | 45 minutes | Sadie, Viktoria, Alberta, Ana(Kiki), Safa, Jess | Yes | Leading part 3 and contributing to the assignment doc
2 | 2025-09-04 | Zoom team call : reviewing work done on parts 1, 2 and 3, discussions and retros; allocating roles for the main app, forming smaller sub-teams to collectively complete complex tasks | 20 minutes | Sadie, Viktoria, Alberta, Ana(Kiki), Safa, Jess | Yes | All roles provisionally assigned
2 | 2025-10-04 | Updated the file in github | 25 mins | Alberta | Yes | Added my card
3 | 16/04/2025 | Zoom team call : receiving feedback from Fredrick on the assignment doc, discussing flow | 30 minutes | Sadie, Viktoria, Alberta, Ana(Kiki), Safa, Jess | Yes | more clarification on allocating tasks and breaking down into smaller groups to start targeted work
4 | 22/04/2025 | Zoom team call : discussing flow and roles to be completed for Friday | 25 mins | Sadie, Viktoria, Alberta, Ana(Kiki), Safa, Jess | Yes | Organised smaller team allocation for tasks
4 | 24/04/2025 | Zoom call to discuss login/sign up backend and frontend build | 20 minutes | Safa, Jessica, Alberta | Yes | Safa & Jess discussed backend, agreed to research comopnents with safa
4 | 25/04/2025 | Discussed with Safa components, split of signup and sign in page | 30 minutes | Alberta & Safa | yes | taking on sign in page and safa will do sign up
5 | 29/04/2025 | Coded the signin page attempted to fix errors | 5 hours | Alberta | Yes | was unable to fix the error
5 | 30/04/2025 | zoom team call with team | 20 mins | Alberta, Viktoria & Sadie | Yes
5 | 30/04/2025 | asked Safa to help with my code as i was having issues and couldn't identify the problem | 10 mins |  | Yes
5 | 2025-01-05 | Zoom call with teams and Sadie helped fix errors and page links in my signin page | 10 mins | Alberta & Sadie | Yes
Total time:

## Activity Log - Safa Zia
Name: |  | Project Group (Name/Number): Group-4-Fullstack
This activity log is for you to document your individual contributions and ideas you have done towards your final group project. This will be submitted to your instructors along with your project code. You can document how many minutes you spent working on your code, when you had team meetings outside of the class sessions, or use this as a way to take notes for your own viewing. This is to be completed individually.
Week: | Date: | Activity/Task: | Time spent on Activity: | Team Members Involved (if applicable) | Completed? | Notes:
1 | 2025-01-04 | Zoom team call to pitch ideas and pick one for the project, initial discussion of assignment requirements and allocation of tasks | 60minutes | Sadie, Viktoria, Alberta, Ana(Kiki), Safa | Yes | Sadie to initiate the assignment document, Viktoria to create a repo, everyone to check out API tools we have selected to use, Kiki to start work on wireframes
2 | 2025-07-04 | Zoom team call : discussing roles for the assignment and areas of focus, reviewing pitch doc and wireframes, planning parts 3 and 4 | 45 minutes | Sadie, Viktoria, Alberta, Ana(Kiki), Safa, Jess | Yes | SQL backend lead and read.me file also working on component.js
2 | 2025-09-04 | Zoom team call : reviewing work done on parts 1, 2 and 3, discussions and retros; allocating roles for the main app, forming smaller sub-teams to collectively complete complex tasks | 20 minutes | Sadie, Viktoria, Alberta, Ana(Kiki), Safa, Jess | Yes | All roles provisionally assigned
3 | 16/4/2025 | Zoom team call : receiving feedback from Fredrick on the assignment doc, discussing flow | 30 minutes | Sadie, Viktoria, Alberta, Ana(Kiki), Safa, Jess | Yes | More clarification on allocating tasks and breaking down into smaller groups to start targeted work
4 | 22/4/2025 | Research on SQL schema and tables needed for app to work, taking into consideration login/register component and arranging meeting for SQL with Jessica | 40 minutes | Safa | Yes | Meeting thurs 24th at 5.30pm to discuss findings
4 | 22/4/2025 | SQL schema written up | 45 minutes | Safa | Yes | First draft od SQL schema
4 | 22/4/2025 | Researching other dependencies such as Axios and bycrypt to work on flow of project between front and back end | 20 minutes | Safa | Yes | Axios maybe useful to retrieve info, bring up in group meeting
4 | 22/4/2025 | Zoom call with team discussing component allocation and architecture | 30 minutes | Sadie, Viktoria, Alberta, Ana(Kiki), Safa, Jess | Yes | Organised smaller team allocation
4 | 23/4/2025 | Writing up other code such as db.js, controller.js, .env update, to integrate with SQL database | 180 minutes | Safa | Yes | Draft code written for linking database and for login/signup
4 | 24/4/2025 | Zoom call to discuss login/sign up backend and frontend build | 20 minutes | Safa, Jessica, Alberta | Yes | Presented code to Jess, agreed to merge and optimise code, agreed to research compnents with alberta and reconvene
4 | 24/4/2025 | Merged SQL and backend code with Jess to create optimised version and reshared with her | 60 minutes | Safa | Yes | Given all clear to push to github
4 | 25/4/2025 | Put code in cloned repo and fixed any errors, needed more files than originally thought (server.js, express.js, db.js, authroutes.js, usercontroller.js) | 3 hours | Safa | Yes | Added all code
4 | 25/4/2025 | Pushed all my code to github and created pull request for new branch - database/setup/safa | 30 minutes | Safa | Yes | Successfully pushed code and created pull request
4 | 25/04/25 | Discussed with alberta the split of signup and sign in page | 30 minutes | safa | yes | decided to take on signup page and alberta will do sign up
4 | 26/04/25 | Coded the signup page and changed some backend logic i previously comitted to work with the new code | 2 hours | Safa | Yes | Code written for sign up ready for css
4 | 26/04/25 | Pushed new code in branch signup/page/safa and merged conflict with configweatherwatch.env.test | 1 hour | Safa | Yes | Created pull request for group to review and merge
4 | 27/04/25 | Wrote the profile page code and linked it to app.js, changed the syntax of db.js to conform with other files | 2 hours | Safa | Yes | Pushed the code for group members assigned to same responsibilities to review
4 | 27/04/25 | Merged Viktorias pull request | 10 minutes | Safa | Yes | Merged into main
5 | 28/04/25 | Group Zoom Call : disussing what is left to build, checking which code in PRs runs with errors and why. | 30 minutes | Safa, Viktoria, Sadie, Alberta and Kiki | Yes | Taken notes on what left to complete
5 | 29/04/25 | Merged server.js and index.js so folder is cleaner | 30 minutes | Safa | Yes | Taken unnecessary code out and pushed
5 | 29/04/25 | Created middleware.js for JWT protection, created doc on JWT use for wider group understanding | 3 hours | Safa | Yes | Pushed the code for group members assigned to same responsibilities to review, uploaded JWT doc on slack
5 | 30/04/25 | README file written up and shared with the group for feedback | 1 hour | Safa | Yes | Shared for group review
5 | 30/04/25 | Looked at alberta's code to ensure compatibilty with sign up code | 30 minutes | Safa | Yes | Given suggestions on how to fix code
5 | 2025-01-04 | Worked through issues on profile/page/branch, pulled from main to get up to speed and merged to resolve any conflicts | 2 hours | Safa | Yes | Pushed for group members to review
5 | 2025-02-04 | Removed lat and longitude being able to be changed from profile page, pushed new updated code to github | 1 hour | Safa | Yes | Pushed for group members to review
5 | 2025-03-04 | Code was still trhoeing up errors, so pushed new changes, Viktoria helped by noticing mismatched is SetToken and UserContext, she then spotted some more errors in the code, e.g PATCH and PUT both being used, she updated the code and fixed these errors | 2 hours | Safa, Viktoria | Yes | Viktoria pushed the code and it was merged by Sadie
5 | 2025-03-04 | Worked on the project document, mainly expanded the conclusion section and fleshed out technologies used | 45 minutes | Safa | Yes | Continuous work needed
5 | 2025-03-04 | Updated README to include instructions on how to run app concurrently | 30 minutes | Safa | Yes | Shared for group review
Total time:

## Activity Log - Jessica James
Name: |  | Project Group (Name/Number): Group-4-Fullstack
This activity log is for you to document your individual contributions and ideas you have done towards your final group project. This will be submitted to your instructors along with your project code. You can document how many minutes you spent working on your code, when you had team meetings outside of the class sessions, or use this as a way to take notes for your own viewing. This is to be completed individually.
Week: | Date: | Activity/Task: | Time spent on Activity: | Team Members Involved (if applicable) | Completed? | Notes:
1 | 2025-01-04 | Zoom team call to pitch ideas and pick one for the project, initial discussion of assignment requirements and allocation of tasks | 60mins | Sadie, Viktoria, Alberta, Ana(Kiki), Safa, Jess | Yes | Sadie to initiate the assignment document, Viktoria to create a repo, everyone to check out API tools we have selected to use, Kiki to start work on wireframes
2 | 2025-07-04 | Zoom team call : discussing roles for the assignment and areas of focus, reviewing pitch doc and wireframes, planning parts 3 and 4 | 45 mins | Sadie, Viktoria, Alberta, Ana(Kiki), Safa, Jess | Yes | SQL backend lead and read.me file also working on component.js
2 | 2025-09-04 | Zoom team call : reviewing work done on parts 1, 2 and 3, discussions and retros; allocating roles for the main app, forming smaller sub-teams to collectively complete complex tasks | 20 minutes | Sadie, Viktoria, Alberta, Ana(Kiki), Safa, Jess | Yes | All roles provisionally assigned
3 | 16/04/2025 | Zoom team call : receiving feedback from Fredrick on the assignment doc, discussing flow | 30 mins | Sadie, Viktoria, Alberta, Ana(Kiki), Safa, Jess | Yes
4 | 22/04/2025 | Research on SQL schema and tables needed for app to work, taking into consideration login/register component and arranging meeting for SQL with Safa | 40 minutes | Jess | Yes
4 | 22/04/2025 | SQL schema written up | 45 minutes | Jess | Yes | First draft od SQL schema
4 | 23/04/25 | Worked on SQL Schema, tried to add some features and prep to send to Safa to Merge | 120 | Jess | Yes
4 | 24/04/2025 | Zoom call to discuss login/sign up backend and frontend build | 20 mins | Safa, Jessica, Alberta | Yes | Met with Safa and discussed the database and we decdied to merge this together and then check over before we push to github
4 | 24/04/2025 | Read over the merged Database that Safa has merged , checked for errors ect | 30 mins | Jess | Yes
4 | 29/04/2025 | Adding the comments to the sql database so it is clear to everyone what is happening at each stage | 60 mins | Jess | Yes | notes added - will finish tomorrow
4 | 30/04/2025 | Adding the comments to the sql database so it is clear to everyone what is happening at each stage | 30 mins | Jess | Yes | finishing today
Total time: